## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2171-swen-261-05-d Footware eStore
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a DEVELOPER I want to REFACTOR THE STOCK CODE so that ITS EASIER TO MANAGE. | GIVEN the shoe exists WHEN I update the shoe THEN the quantity of it should update by 1 | Pass | MO; 2/05;
As a USER I want to BE ABLE TO LOGIN TO MY ACCOUNT, CREATE AN ACCOUNT, UPDATE MY ACCOUNT, OR DELETE MY ACCOUNT so that ACCESS SPECIAL FEATURES ON THE SITE. | 1. GIVEN I submit a HTTP GET request for the list of accounts WHEN products exist in the list of accounts THEN the system should return a list of accounts and a status code of 200 (OK) | Pass | MO; 2/05;
| 2. GIVEN I submit a HTTP GET request for the list of accounts WHEN no accounts exist in the list of accounts THEN the system should return an empty list of shoes and a status code of 200 (OK) | Pass | MO; 2/05;
| 3. GIVEN I submit a HTTP POST request for a shoe object WHEN that shoe doesn't exist THEN the system should create the account, add it to the list of accounts , save to the persistent store, and return the account object and a status code of 201 (CREATED) | Pass | MO; 2/05;
| 4. GIVEN I pass a HTTP GET request a account username WHEN the account with the given id exists THEN the system should return the account with the status code of 200 otherwise 404 if it doesn't exist | Pass | MO; 2/05;
| 5. GIVEN I submit a HTTP POST request for a account object WHEN the account already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | MO; 2/05;
| 6. GIVEN I submit a HTTP DELETE request to delete an account in the list of accounts WHEN the account exist in the list of accounts THEN the system should delete that account and return a status code of 200 (OK) | Pass | MO; 2/05;
| 7. GIVEN I submit a HTTP DELETE request to delete an account in the list of accounts WHEN the account doesn't exist in the list of accounts THEN return a status code of (NOT_FOUND) | Pass | MO; 2/05;
| 8. GIVEN I submit a HTTP UPDATE request for account object with a certain username WHEN said account exists in the list of accounts THEN the system should return the updated account and a status code of 200 (OK) | Pass | MO; 2/05;
| 9. GIVEN I submit a HTTP UPDATE request for account object with a certain username WHEN said account doesn't exist in the list of accounts THEN the system should return a status code of NOT_FOUND | Pass | MO; 2/05;
| 10. GIVEN I submit a string request for the list of accounts WHEN accounts that contain that string exist in the list of accounts THEN the system should return a list of those accounts and a status code of 200 (OK) | Pass | MO; 2/05;
| 11. GIVEN I submit a string request for the list of accounts WHEN there are no accounts that contain that string exist in the list of accounts THEN the system should return an empty list and a status code of 200 (OK) | Pass | MO; 2/05;
As a CUSTOMER I want to GET, ADD, DELETE, AND UPDATE ITEMS IN MY CART so that CAN CHECKOUT THE PRODUCTS I WANT. | 1. GIVEN I submit a HTTP GET request for the cart WHEN products exist in the cart THEN the system should return a list of shoes and a status code of 200 (OK) | Pass | MO; 2/05;
| 2. GIVEN I submit a HTTP GET request for the cart WHEN no shoes exist in the cart THEN the system should return an empty list of shoes and a status code of 200 (OK) | Pass | MO; 2/05;
| 3. GIVEN I submit a HTTP POST request for a shoe object WHEN that shoe doesn't exist THEN the system should create the shoe, add it to the cart, save to the persistent store, and return the shoe object and a status code of 201 (CREATED) | Pass | MO; 2/05;
| 4. GIVEN I pass a HTTP GET request a shoe id WHEN the shoe with the given id exists THEN the system should return the shoe with the status code of 200 otherwise 404 if it doesn't exist | Pass | MO; 2/05;
| 5. GIVEN I submit a HTTP POST request for a shoe object WHEN the shoe already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | MO; 2/05;
| 6. GIVEN I submit a HTTP DELETE request to delete an shoe in the cart WHEN the shoe exist in the cart THEN the system should delete that shoe and return a status code of 200 (OK) | Pass | MO; 2/05;
| 7. GIVEN I submit a HTTP DELETE request to delete an shoe in the cart WHEN shoe doesn't exist in the cart THEN return a status code of (NOT_FOUND) | Pass | MO; 2/05;
| 8. GIVEN I submit a HTTP UPDATE request for shoe object with a certain ID WHEN said shoe exists in the cart THEN the system should return the updated shoe and a status code of 200 (OK) | Pass | MO; 2/05;
| 9. GIVEN I submit a HTTP UPDATE request for shoe object with a certain ID WHEN said shoe doesn't exists in the cart THEN the system should return a status code of NOT_FOUND | Pass | MO; 2/05;
| 10. GIVEN I submit a string request for the cart WHEN shoes that contain that string exist in the cart THEN the system should return a list of those shoes and a status code of 200 (OK) | Pass | MO; 2/05;
| 11. GIVEN I submit a string request for the cart WHEN there are no shoes that contain that string exist in the cart THEN the system should return an empty list and a status code of 200 (OK) | Pass | MO; 2/05;
As a CUSTOMER I want to GET, ADD, DELETE, AND UPDATE ITEMS IN MY Wish-list so that SO I CAN BUY THEM WHEN THE PRICE DROPS. | 1. GIVEN I submit a HTTP GET request for the wish-list WHEN products exist in the wish-list THEN the system should return a list of shoes and a status code of 200 (OK) | Pass | MO; 2/05;
| 2. GIVEN I submit a HTTP GET request for the wish-list WHEN no shoes exist in the wish-list THEN the system should return an empty list of shoes and a status code of 200 (OK) | Pass | MO; 2/05;
| 3. GIVEN I submit a HTTP POST request for a shoe object WHEN that shoe doesn't exist THEN the system should create the shoe, add it to the wish-list , save to the persistent store, and return the shoe object and a status code of 201 (CREATED) | Pass | MO; 2/05;
| 4. GIVEN I pass a HTTP GET request a shoe id WHEN the shoe with the given id exists THEN the system should return the shoe with the status code of 200 otherwise 404 if it doesn't exist | Pass | MO; 2/05;
| 5. GIVEN I submit a HTTP POST request for a shoe object WHEN the shoe already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | MO; 2/05;
| 6. GIVEN I submit a HTTP DELETE request to delete an shoe in the wish-list WHEN the shoe exist in the wish-list THEN the system should delete that shoe and return a status code of 200 (OK) | Pass | MO; 2/05;
| 7. GIVEN I submit a HTTP DELETE request to delete an shoe in the wish-list WHEN shoe doesn't exist in the wish-list THEN return a status code of (NOT_FOUND) | Pass | MO; 2/05;
| 8. GIVEN I submit a HTTP UPDATE request for shoe object with a certain ID WHEN said shoe exists in the wish-list THEN the system should return the updated shoe and a status code of 200 (OK) | Pass | MO; 2/05;
| 9. GIVEN I submit a HTTP UPDATE request for shoe object with a certain ID WHEN said shoe doesn't exists in the wish-list THEN the system should return a status code of NOT_FOUND | Pass | MO; 2/05;
| 10. GIVEN I submit a string request for the wish-list WHEN shoes that contain that string exist in the wish-list THEN the system should return a list of those shoes and a status code of 200 (OK) | Pass | MO; 2/05;
| 11. GIVEN I submit a string request for the wish-list WHEN there are no shoes that contain that string exist in the wish-list THEN the system should return an empty list and a status code of 200 (OK) | Pass | MO; 2/05;
As a DEVELOPER I want to MAKE A SHOE COMPONENT so that THE ADMIN CAN MAKE AND MODIFY SHOE PRODUCTS. | GIVEN THE ANGULAR PROJECT IS RUNNING WHEN I OPEN THE LOCAL HOST THEN I SHOULD SEE A SHOE OBJECT. | Pass | MZ; 3/14
As a ADMIN I want to SEE A LIST OF ALL MY PRODUCTS so that I CAN ACCESS THEM INDIVIDUALLY. | GIVEN I am on e-store site WHEN I navigate the inventory page THEN I expect all the shoes to see a list of shoes I can choose from | Pass | Mz; 3/14
As the ADMIN I want to BE ABLE TO MODIFY THE PRICE, QUANTITY OF THE SHOE so that I CAN RESTOCK OR GIVE DISCOUNTS ON MY PRODUCTS | GIVEN I am viewing the details of a shoe WHEN I edit the information about the product THEN I expect the details to be updated. | Pass | MZ; 3/14
As a DEVELOPER I want to THE SITE TO SEND REQUESTS TO THE SERVER so that SO THAT THE SERVER CAN HAVE THE RESPONSIBILITY OF MANAGING DATA | GIVEN that the website is server is running WHEN I am interacting with the website THEN I expect messages to appear to tell me what is occurring. | Pass | MZ; 3/14
As a Developer I want to be able to give my customers navigation so that there can be a ease of access for the customers. | GIVEN there are multiple pages available, WHEN I visit the website, THEN I expect to find a way to navigate to and view them. | Pass | MZ; 3/14
As a DEVELOPER I want to THE SITE TO SEND REQUESTS TO THE SERVER so that SO THAT THE SERVER CAN HAVE THE RESPONSIBILITY OF MANAGING DATA | GIVEN the REST API server is running WHEN I connect the website I THEN I expect see a search box and a list of shoes from the server loaded on the page. | Pass | MZ; 3/14
| GIVEN the REST API server is running WHEN I connect the inventory I THEN I expect see a list of shoes from the server loaded on the page. | Pass | MZ; 3/14
| GIVEN the REST API server is running WHEN I connect the inventory and click on a shoe I THEN I expect to see and access the details of the shoe | Pass | MZ; 3/14
| GIVEN the REST API server is running WHEN I connect the inventory and click on a shoe I THEN I expect to be able to edit the details of the shoe and save it to the server | Pass | MZ; 3/14
| GIVEN the REST API server is running WHEN I connect the inventory I THEN I expect see an option to create a shoe | Pass | MZ; 3/14
| GIVEN the REST API server is running WHEN I create a shoeTHEN I expect for it to be added to the inventory, and I expect to be able to access it | Pass | MZ; 3/14
As a USER I want to BE ABLE TO LOGIN TO MY ACCOUNT, CREATE AN ACCOUNT, UPDATE MY ACCOUNT, OR DELETE MY ACCOUNT so that ACCESS SPECIAL FEATURES ON THE SITE. | GIVEN I am at the login page WHEN I want to create an account THEN I expect to see an option to sign up | Pass | MZ; 3/14
| GIVEN I am at the login page WHEN I create an account THEN I expect to be have my account created and be able to sign into it immediately | Pass | MZ; 3/14
| GIVEN I am at the login page WHEN I update an account's username or display name THEN I expect the display name or username to be changed | Pass | MZ; 3/14
| GIVEN I am at the login page WHEN I delete an account THEN I expect to be logged out with the account gone | Pass | MZ; 3/14
| GIVEN I am logged into my account WHEN I navigate the website THEN I expect to be logged into my account still | Pass | MZ; 3/14
| GIVEN I log out of my account WHEN I navigate the website THEN I expect for the website to no longer save or have my data | Pass | MZ; 3/14
| GIVEN I am logged into an Admin Account WHEN I go to the inventory page THEN I expect to see the option to edit the inventory and its contents | Pass | MZ; 3/14
| GIVEN I am logged into a non-admin account WHEN I to the inventory THEN I expect for the website to not allow me to delete from the inventory or modify a shoes price or quantity | Pass | MZ; 3/14
As a CUSTOMER I want to HAVE A CART WHERE I CAN STORE SHOES FROM THE INVENTORY so that CHECKOUT THEM OUT ALL AT ONCE. | GIVEN If I am logged into an Admin account WHEN I connect the website I THEN I expect not to see a way to navigate to the cart page | Pass | MZ; 3/15
| GIVEN If I am logged into an account that isn't an Admin account WHEN I connect the website THEN I expect to see a way to navigate to the cart page | Pass | MZ; 3/15
| GIVEN If I am logged into an account that isn't an Admin account WHEN I go to the cart page THEN I expect to see the list of shoes I have saved into my cart | Pass | MZ; 3/15
| GIVEN If I am logged into an account that isn't an Admin account WHEN I go to the cart page THEN I expect an option to remove shoes from my cart | Pass | MZ; 3/15
| GIVEN If I am logged into an account that isn't an Admin account WHEN remove a shoe from my cart THEN I expect for it to be gone from my cart and stored back into the inventory | Pass | MZ; 3/15
| GIVEN If I am logged into an account that isn't an Admin account WHEN I click on a shoe in the inventory THEN I expect to see an option to add the shoe into my account, and have that shoe be there when I go to my cart page | Pass | MZ; 3/15
| GIVEN If I am logged into an account that isn't an Admin account WHEN I click on a shoe on my cart page THEN I expect to be able to change the shoe size or color | Pass | MZ; 3/15
As a customer, I want to save items to my wishlist so that I can receive updates when the price changes. | Given I want to add an item to my wishlist, when I click on an add option I expect that item to be saved. | Pass | MO; 3/30
| Given there is a price change on a product I am watching, when this happens, I expect to recive a notification. | Pass | MO; 3/30
| Given an item is purchaced or removed from the site, when I view my wishlist I expect the show to be gone. | Pass | MO; 3/30
| Given I no longer want to watch a shoe, when I click remove I expect the shoe to be removed from my wishlist. | Pass | MO; 3/30
| Given I want to purchace a shoe on my wishlist, when I click add to cart, I expect the shoe to be moved to my cart. | Pass | MO; 3/30
As a customer I want to check out items in my cart so I can own them, and empty my shopping cart. | Given I bring items from the shopping cart, when I click checkout I expect to see a total cost. | Pass | MO; 3/30
| Given I bring items from the shopping cart, when I click checkout I expect to see a field to provide my shipping information. | Pass | MO; 3/30
| Given I bring items from the shopping cart, when I click checkout I expect the items to be removed from my cart. | Pass | MO; 3/30
| Given I purchace some shoes, when I click checkout I expect the shoes to be added to my purchace history. | Pass | MO; 3/30
As an Owner I want to create coupons and discounts so I can give my customers an incentive to buy more stuff | Given I am on my admin profile page when I click add coupon, I expect a coupon to be added with the discount value and code I enter. | Pass | MZ; 3/30
| Given I am a customer, when I click on the checkout page I expect see an option to enter a cupon. | Pass | MZ; 3/30
| Given I enter a valid coupon, I expect the price of the purchase to be affected. | Pass | MZ; 3/30
| Given I am an admin and no longer want to have a coupon available, when I click a delete option, I expect the cupon to be removed from the system. | Pass | MZ; 3/30
As a Customer I want to be able to view my past purchases and current products in process so I can keep track of what I’m spending. | Given I am on my profile, when I scroll down I expect to see a section about my order history. | Pass | MO; 3/30
| Given I want to view more information, when I click on a shoe, I expect to see transaction and product details. | Pass | MO; 3/30
As an Owner I want to see transactions so I can get the product shipped and track the business's health. | Given there is a shoe to ship, when I click on an order I expect to see details about the purchase. | Pass | MO; 3/30
| Given there is a shoe to ship, when I click on an order I expect to see shipping information. | Pass | MO; 3/30
| Given there is a transaction, when I click on the transactions page I expect all transactions to visable, from all cusormers. | Pass | MO; 3/30
| Given there is a transaction, when I click on the transactions page I expect the page to be updated with this recent transaction. | Pass | MO; 3/30
As a customer I want to apply coupons at checkout to reduce the cost of the items in my cart | Given I am a customer and have a coupon available, when I add it to my cart, then the price of my cart will go down | Pass | MZ; 3/30